Planning Fill-in Form

Goal
Measures
Timescale


Modeling early language games
Comparison with actual parent-child dialogues
12 weeks


Objectives
Measures
Timescale


1. Preparation
Orientation
5 days


2. Corpora / representation
Data for model
6 days


3. Implement response generation mechanism
Implementation of model
9 days


4. Evaluate
Assessment of model
3 days


5. Report

6 days


Tasks
Measures
Timescale

1.1 Literature study
Increased understanding
3 days

1.2 Select corpora
Dialogue fragments that will be used as seed for model
2 days

2.1 Design representation
A representation adequate to model these dialogues
2 days

2.2 Annotate corpora
Application of this representation to the data collected
4 days

3.1 Implement analysis of parent utterances
Interpreting parent utterances in the selected representation
4 days

3.2 Implement child responses
Transforming the representations into novel responses
5 days

4.1 Comparison with actual parent-child dialogues
Subjective judgement of plausibility
3 days

5.1 Write report and presentation

6 days

